## Slide 1: ADAC Annual Meeting Marine IP - Detection and Mapping of Oil Under Ice: A Ruggedized Field Kit
Researcher Kari Walker, IntelliSense Marine LLC
PI Dr. Scott Socolofsky, Texas A&M University

## Slide 2: ADAC Project: Marine Induced Polarization Methods for the Detection and Mapping of Oil in an Arctic Marine Oil Spill – Ruggedized Field Kit Production and Testing
• Project Principal Investigator: Dr. Scott Socolofsky, Texas A&M University
• Supporting Team:
  Ms. Kari Walker and Mr. Kevin Hand, IntelliSense Marine
  Mr. Art Wright, Mr. Jay Radler and Mr. Todd Stedman, Induced Polarization Associates
  Mr. Nathan Lamie, Lead Engineer/Facility Operator, Cold Regions Research and Engineering Laboratory, U.S. Army Corps of Engineers
• Project Champion: LCDR Clifton Graham, CG-MER
ADAC Annual Meeting: 03 June 2021

## Slide 3: Marine IP: Project Description and Baseline
Project Description: Federal on-scene spill responders need remote sensing tools to detect and map oil in the open-Arctic ocean, broken ice fields, as well as oil under and within ice.
This research effort will build and test hardware and software for an Arctic-Ready Marine Induced Polarization (Marine IP) System, which locates and assesses polarizable mineral and particle distributions - such as hydrocarbons - in water, ice and in sediment.
Baseline: Marine IP has shown strong promise to serve as a tool for the detection and mapping of oil under ice and in seafloor sediment. A robust, Arctic-Ready Marine IP system needs to be developed to mitigate the harsh conditions of the Arctic.
ADAC Annual Meeting: 03 June 2021

## Slide 4: Marine IP: Method
Oil on and within seafloor sediment:
A cable is towed behind a vessel
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the return signal caused by substances encountered
Receiver Electrodes
Oil
Transmit Electrodes
Depressor
ADAC Annual Meeting: 03 June 2021

## Slide 5: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility
A cable streamed under tank ice
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the signal due to substances encountered
ADAC Annual Meeting: 03 June 2021
Induced Polarization Streamer Tail
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail

## Slide 6: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility:
Tests will be conducted using shared oil under ice conditions:
  Existing oil placement will be well documented
  Additional oil will be added under and encapsulated within the ice
ADAC Annual Meeting: 03 June 2021
CRREL Testing Facility
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail

## Slide 7: Marine IP: Progress on Research Objectives
Project Objectives:
Continue to validate Marine IP as a viable means to detect oil within ice and broken ice: Y8, no-cost extension due to COVID-19 delays
Develop and build the hardware, firmware and software for an Arctic-Ready Marine IP System that can withstand the harsh environment of the Arctic: Y8, no-cost extension
Test the Arctic-Ready Marine IP System in an offshore, towed scenario: Y8, no-cost extension
Test the Arctic-Ready Marine IP System in a simulated Arctic environment scenario (CRREL): Y8, no-cost extension
Further identify possible Marine IP deployment mechanisms for characterization, with emphasis on AUVs: June 30
ADAC Annual Meeting: 03 June 2021
Old Enclosure
New Enclosure

## Slide 8: Marine IP: Progress on Remaining Year 6 Objectives
Remaining Project Objectives:
Investigate the potential of Marine IP to detect oil in partial ice formations as well as under pack ice.
Investigate and determine Marine IP’s effectiveness to accurately detect the extent of contaminated areas.
Remaining Project Milestones:
Determine the spectral signature of selected target contaminants utilizing a Marine IP system.
Complete data analysis and reporting.
ADAC Annual Meeting: 03 June 2021
Old System
New System

## Slide 9: Marine IP: Planned Field Work
Oil-Under-Ice testing: CRREL Testing Facility
Tests using shared oil under ice conditions:
ADAC Annual Meeting: 03 June 2021
CRREL Testing Facility
Open Water Testing: Puget Sound
Tests on a vessel in Puget Sound, WA:
Delayed to Year 8 – No-cost extension due to COVID-19

## Slide 10: Marine IP: Progress on Milestones
Project Milestones – Hardware Design
Outline of general design requirements. Complete
ADAC Quarterly Review: 29 Apr 2021

## Slide 11: Marine IP: Progress on Milestones
Project Milestones – Hardware Design
High-level block diagrams for device prototype. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 12: Marine IP: Progress on Milestones
Project Milestones – Hardware Design
Laboratory testing device design drawings. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 13: Marine IP: Progress on Milestones
Project Milestones – Software Design
Engineering report outlining requirement and specification details. Complete
Develop a plan-design-implement-test-revise loop. Complete
Select a suite of core usage and testing cases. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 14: Marine IP: Progress on Milestones
Procure and test components for functional performance in the laboratory on small-scale. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 15: Marine IP: Progress on Milestones
Complete any preliminary revisions to hardware design based on laboratory tests of components. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 16: Marine IP: Progress on Milestones
PCB and Offboard BOMs
Assemble Bill of Materials. Complete
ADAC Annual Meeting: 03 June 2021

## Slide 17: Marine IP: Progress on Milestones
Assemble final design drawings for prototype. Complete
Finalized, Compiled Board Design
21 Board Component Designs
ADAC Annual Meeting: 03 June 2021

## Slide 18: Marine IP: Progress on Milestones
  Fabricate prototype: internal boards. Complete
Finalized, Compiled Board Design
ADAC Annual Meeting: 03 June 2021
Custom build of electronic boards complete.

## Slide 19: Marine IP: Progress on Milestones
Design and write prototype firmware. 80% Complete
  Working to complete Transmitter Microcontroller, Touch UI Display
ADAC Annual Meeting: 03 June 2021

## Slide 20: Marine IP: Progress on Milestones
  Complete designs for device enclosure and off-board wiring schemes. Complete
New Enclosure
ADAC Annual Meeting: 03 June 2021
Old Enclosure
24’’
12’’
24’’
18.5’’
6.9’’
14’’
Interior Interface Layout Design
Back Case Exterior
Front Case Exterior
Left Case Exterior
Right Case Exterior

## Slide 21: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
ADAC Annual Meeting: 03 June 2021
Build.
Design.

## Slide 22: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
ADAC Annual Meeting: 03 June 2021
Laptop
New Marine IP Enclosure
Marine IP Cable
GPS

## Slide 23: Marine IP: Progress on Milestones
Mock-up a user interface and menu structure. Complete
Submit Field Test Plans for HQ USCG Project Champion review and approval. June 30
Complete mockups of user interfaces and software control systems. June 30
Submit engineering report reviewing design, fabrication methods, construction, and initial performance reviews of hardware system. June 30
Firmware developed and undergoing small-scale laboratory tests and bug fixes. Y8, summer
Startup and initial performance and function tests. Y8, summer Hardware Complete. Pending firmware.
Complete performance and functional tests in laboratory. Y8, summer. Pending firmware.
ADAC Annual Meeting: 03 June 2021

## Slide 24: Marine IP: Progress on Milestones
Hardware: Beach testing of device and its integrations with the Marine IP cables. Y8, summer, due to COVID-related board manufacturing delays.
Complete implementation of Arctic-Ready Marine IP System – Hardware, Software. Y8
Complete Field Trials of Arctic-Ready Marine IP System. Y8
Complete data analysis and reporting. Y8
ADAC Annual Meeting: 03 June 2021

## Slide 25: Marine IP: Progress on Outcomes/Outputs
  Provide test plan for Arctic-Ready Marine IP System. June 30
Engineering Design Report: Provide advanced information for the design parameters for applications of Marine IP with an autonomous underwater vehicle (AUV). June 30
Arctic-Ready Marine IP System – Hardware: Provide a Marine IP measurement field kit designed for use in arctic conditions. Y8, no-cost extension due to COVID-19.
Arctic-Ready Marine IP System – Software: Provide a new software interface for data collection using the Marine IP measurement field kit. Y8
Technical Report: Provide DHS with a report with all the results of this research that becomes publicly available. Y8, items to follow completion of field work.
Peer-Reviewed Publications: Research team will produce draft peer-reviewed scientific publications from this project. Y8
Publicly Available Data: Researchers (in coordination with ADAC) will ensure all releasable data produced during this project is publicly available within 6 months of project conclusion. Y8
ADAC Annual Meeting: 03 June 2021

## Slide 26: Marine IP: Student Contributions
Students did not contribute to this research
One full-time employee and one part-time employee support this project, driving cable design, build, and testing, as well as supporting data processing and analysis
ADAC Annual Meeting: 03 June 2021

## Slide 27: Marine IP: Update on Transition and TRL
The goal of this research is to demonstrate Marine IP technology in a relevant environment to enhance situational awareness for the USCG, DHS and other agencies relating to oil released in open or ice-laden water.
Steps to transition:
Demonstration of value and effectiveness for the USCG and other stakeholders through open water and simulated ice environment testing – ADAC Year 6 research.
Development of commercialized equipment, ruggedized for the Arctic environment – ADAC Year 7-8 research.
Develop a software interface suitable for USCG usage – ADAC Year 7-8 research.
ADAC Annual Meeting: 03 June 2021

## Slide 28: Marine IP: Questions?
Feedback…
What are we missing?
What can we improve?
Who should we connect with to improve odds of research success?
Project team at CRREL during baseline testing.
From L to R: Karin Messenger (USCG), Scott Socolofsky (TA&M), Dana Tulis (USCG), Alexander Balsley (USCG R&D), Kari Walker (Marine IP), Nathan Lamie (CRREL)
ADAC Annual Meeting: 03 June 2021