## Slide 1: ADAC Annual Meeting Marine IP - Detection and Mapping of Oil Under Ice: A Ruggedized Field Kit
PI Dr. Scott Socolofsky, Texas A&M University
Researcher Kari Walker, IntelliSense Marine LLC

## Slide 2: ADAC Project: Marine Induced Polarization Methods for the Detection and Mapping of Oil in an Arctic Marine Oil Spill – Ruggedized Field Kit Production and Testing
• Project Principal Investigator: Dr. Scott Socolofsky, Texas A&M University
• Supporting Team:
  Ms. Kari Walker and Mr. Kevin Hand, IntelliSense Marine
  Mr. Art Wright, Mr. Jay Radler and Mr. Todd Stedman, Induced Polarization Associates
  Mr. Nathan Lamie, Lead Engineer/Facility Operator, Cold Regions Research and Engineering Laboratory, U.S. Army Corps of Engineers
• Project Champion: LCDR Clifton Graham, CG-MER
ADAC Annual Meeting: 21 April 2022

## Slide 3: Marine IP: Project Description and Baseline
Project Description: Federal on-scene spill responders need remote sensing tools to detect and map oil in the open-Arctic ocean, broken ice fields, as well as oil under and within ice.
This research effort will build and test hardware and software for an Arctic-Ready Marine Induced Polarization (Marine IP) System, which locates and assesses polarizable mineral and particle distributions - such as hydrocarbons - in water, ice and in sediment.
Baseline: Marine IP has shown strong promise to serve as a tool for the detection and mapping of oil under ice and in seafloor sediment. A robust, Arctic-Ready Marine IP system needs to be developed to mitigate the harsh conditions of the Arctic.
ADAC Annual Meeting: 21 April 2022

## Slide 4: Marine IP: Method
Oil on and within seafloor sediment:
A cable is towed behind a vessel
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the return signal caused by substances encountered
Receiver Electrodes
Oil
Transmit Electrodes
Depressor
ADAC Annual Meeting: 21 April 2022

## Slide 5: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility
A cable streamed under tank ice
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the signal due to substances encountered
Induced Polarization Streamer Tail
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail
ADAC Annual Meeting: 21 April 2022

## Slide 6: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility:
Study design included 6 test scenarios:
  Oil under solid ice
  Oil encapsulated within ice
  Oil in pockets under broken and refrozen ice.
  Oil in broken ice
  Controls: Broken ice and solid ice, no oil added
CRREL Testing Facility
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail
ADAC Annual Meeting: 21 April 2022

## Slide 7: Marine IP: Progress on Research Objectives
Project Objectives:
Continue to validate Marine IP as a viable means to detect oil within ice and broken ice. Complete
Develop and build the hardware, firmware and software for an Arctic-Ready Marine IP System that can withstand the harsh environment of the Arctic: Complete
Test the Arctic-Ready Marine IP System in an offshore, towed scenario: Complete
Test the Arctic-Ready Marine IP System in a simulated Arctic environment scenario (CRREL): Complete
Further identify possible Marine IP deployment mechanisms for characterization, with emphasis on AUVs: Complete
Old Enclosure
New Enclosure
ADAC Annual Meeting: 21 April 2022

## Slide 8: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
Build.
Design.
Custom build of electronic boards complete.
Project Milestones – Hardware Designed and Built
ADAC Annual Meeting: 21 April 2022

## Slide 9: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
Laptop
New Marine IP Enclosure
Marine IP Cable
GPS
ADAC Annual Meeting: 21 April 2022

## Slide 10: Marine IP: Progress on Milestones
Design and write prototype firmware. Complete
Firmware developed and undergoing small-scale laboratory tests and bug fixes. Complete
Display Interface: Build
Display Interface: Design
ADAC Annual Meeting: 21 April 2022

## Slide 11: Marine IP: Progress on Milestones
Project Milestones – Software Design Complete
Engineering report outlining requirement and specification details. Complete
Develop a plan-design-implement-test-revise loop. Complete
Select a suite of core usage and testing cases. Complete
Design.
ADAC Annual Meeting: 21 April 2022

## Slide 12: Marine IP: Progress on Milestones
Project Milestones – Software Build Complete
Mock-up a user interface and menu structure. Complete
Complete mockups of user interfaces and software control systems. Complete
Design.
Build.
ADAC Annual Meeting: 21 April 2022

## Slide 13: Marine IP: Progress on Milestones
Submit engineering report reviewing design, fabrication methods, construction, and initial performance reviews of hardware system. Complete
ADAC Annual Meeting: 21 April 2022

## Slide 14: Marine IP: Progress on Milestones
Startup and initial performance and function tests. Complete
Complete performance and functional tests in laboratory. Complete
ADAC Annual Meeting: 21 April 2022

## Slide 15: Marine IP: Progress on Milestones
Hardware: Beach testing of device and its integrations with the Marine IP cables. Complete
ADAC Annual Meeting: 21 April 2022

## Slide 16: Marine IP: Progress on Milestones
Submit Field Test Plans for HQ USCG Project Champion review and approval. April 2022
  Demonstration planned for May 2nd with Coast Guard LCDR Clifton Graham and a NOAA representative in attendance.
ADAC Annual Meeting: 21 April 2022

## Slide 17: Marine IP: Progress on Milestones
Complete implementation of Arctic-Ready Marine IP System – Hardware, Software. Complete
ADAC Annual Meeting: 21 April 2022

## Slide 18: Marine IP: Progress on Milestones
Complete Field Trials of Arctic-Ready Marine IP System. Complete
Complete data analysis and reporting. April 30
ADAC Annual Meeting: 21 April 2022

## Slide 19: Marine IP: Progress on Outcomes/Outputs
  Provide test plan for Arctic-Ready Marine IP System. Complete
Engineering Design Report: Provide advanced information for the design parameters for applications of Marine IP with an autonomous underwater vehicle (AUV). Complete
Arctic-Ready Marine IP System – Hardware: Provide a Marine IP measurement field kit designed for use in arctic conditions. Complete
Arctic-Ready Marine IP System – Software: Provide a new software interface for data collection using the Marine IP measurement field kit. Complete
Technical Report: Provide DHS with a report with all the results of this research that becomes publicly available. April 30
Peer-Reviewed Publications: Research team will produce draft peer-reviewed scientific publications from this project. Intended
Publicly Available Data: Researchers (in coordination with ADAC) will ensure all releasable data produced during this project is publicly available within 6 months of project conclusion. April 30 `
ADAC Annual Meeting: 21 April 2022

## Slide 20: Marine IP: Student Contributions
Students did not contribute to this research
One full-time employee and one part-time employee support this project, driving cable design, build, and testing, as well as supporting data processing and analysis
ADAC Annual Meeting: 21 April 2022

## Slide 21: Marine IP: Update on Transition and TRL
The goal of this research is to demonstrate Marine IP technology in a relevant environment to enhance situational awareness for the USCG, DHS and other agencies relating to oil released in open or ice-laden water.
Steps to transition:
Demonstration of value and effectiveness for the USCG and other stakeholders through open water and simulated ice environment testing – ADAC Year 6 research.
Development of commercialized equipment, ruggedized for the Arctic environment – ADAC Year 7-8 research.
Develop a software interface suitable for USCG usage – ADAC Year 7-8 research.
ADAC Annual Meeting: 21 April 2022

## Slide 22: Marine IP: Next Steps…
Improved signal clarity
Improved post processing software
Testing range of oils
Autonomous operating system
Configure hardware for AUV and buoy deployment
Test in diverse environments
Test on the U.S. Coast Guard Cutter Healy
Project team at CRREL during baseline testing.
From L to R: Karin Messenger (USCG), Scott Socolofsky (TA&M), Dana Tulis (USCG), Alexander Balsley (USCG R&D), Kari Walker (Marine IP), Nathan Lamie (CRREL)
ADAC Annual Meeting: 21 April 2022
Questions?