## Slide 1: ADAC Annual Meeting Project Briefing: Mitigating the Damage to Arctic Copepods from Surface Oil Spills: When to Apply Dispersants.
PI: Dr. Christoph Aeppli, caeppli@bigelow.org
Co-PI: Dr. David Fields, dflelds@bigelow.org
Technicians: Maura Niemisto, Phoebe Keys, Erin Beirne Student Participants: Cameron Carlson/Sam McNeely
Project Champion: CAPT Kirsten R. Trego
Advisory Group: Dr. Robyn Conmy, EPA
Greg Hall USCG Academy Sarah Allan NOAA
1 mm

## Slide 2
Calanus
finmarchicus
Calanus marshallae
Why Calanus finmarchicus?
Calanus hyperboreus
Calanus glacialis

## Slide 3: Copepods are the base of the Arctic food web.
ADAC Program Year 6 Annual Meeting 14 May 2020
Pollock
Ringed Seal
Arctic Tern
Bow Whale
Beluga Whale
Polar Bear
Walrus
Char
Arctic Cod
Alaskan Salmon

## Slide 4: Good Copepod year – Good fish year
ADAC Program Year 6 Annual Meeting 14 May 2020
Laura Sanvicente-Añorve et al, 2006 Hydrobiologia

## Slide 5: Distribution Temporal/Spatial
Previous experiments have placed copepods in jars with oil. No chance for the animals to avoid the spill.
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 6: Mitigating the Damage to Arctic Copepods from Surface Oil Spills: When to Apply Dispersants.
Project goal: To create a set of knowledge products that inform decision-making about when to apply dispersants after an oil spill to minimize damage to the base of the food chain. Specificlly, we focus on zooplankton (copepods).
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 7: OBJECTIVES
In laboratory mesocosm experiments we address the following three objectives:
Objective 1: Determine whether C. finmarchicus copepods actively and effectively avoid oil in mesocosm experiments (Phase I)
Objective 2: Investigate how dispersants influence the exposure of subsurface animals to oil products (Phase II).
Objective 3: Determine how water column stratification the contact between copepods and oil (with and without dispersants) (Phase III)
200 cm
25 cm
oil
Oil layer
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 8: Progress in meeting research objectives
Copepod Towers Constructed
Video IR Setup
copepod tower
copepod in tower
Calanus copepod
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 9: Progress in meeting research objectives
Chemical Sampling and Analytical Method Optimized
Copepods Collected and maintained in the Lab
Sample collection and SPME-GC/MS analysis
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 10
1
2
3
4
5
6
OBJECTIVE 1
Determine whether copepods actively and effectively avoid oil in mesocosm experiments (Phase I)
ADAC Program Year 6 Annual Meeting 14 May 2020
4 cameras – each visualize 10 l
Video recorded at 1 Hz simultaneously from all cameras
Lighting is done using IR lights
Oil concentration measured from 5 sampling ports

## Slide 11
thermocline
1
2
3
4
5
6
Copepods are counted in each field of view to determine change in vertical distribution.
Oil
OBJECTIVE 1
Determine whether copepods actively and effectively avoid oil in mesocosm experiments (Phase I)
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 12: RESULTS
NO OIL:
Copepod distribution within the water column remained stable during the 24-hour control run
OIL ADDITION:
Copepods react immediately to oil in all observed depths
Total copepod abundance drops by 72% in the first 4 hour
Results indicate that the copepod behavior is influenced by the presence of low concentrations of oil
CONTROL
+Oil
Next Step: Confirmatory experiments; Synthesis of all data (manuscript)
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 13: Results Hydrocarbon gradient, no dispersants
6h
2h
0h
24h
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 14
OBJECTIVE 2: Determine the influence of dispersant on the veritical movement of copepods (Phase II)
 Suitable conditions to produce hydrocarbon gradients with dispersed oil has been identified
added airstream as energy to disperse oil
oil/dispersant mixture rapidly disperses, and forms a “cloud” that travels down the column within approx. 6 hours
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 15
droplet size distribution and oil concentration measured by light (left) and fluorescence (right) microscopy
Method: Measurement of Droplet Size Distribution
Next Step: Experiments with life copepods and oil/dispersants
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 16: Methods: Creating a Thermocline
OBJECTIVE 3: Determine the influence of water column stratification on contact between copepods and oil (with and w/o oil; Phase III)
Next Step: Experiments with copepods and (i) oil/dispersants (ii) oil-only
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 17: Year 6 Milestones: Current Status
MILESTONES METRICS
Phase I: Oil avoidance of copepods 80% in progress
Task 1: Copepod tower construction & optimization 100% completed  presented to Advisory group in Oct.; decision to go forward ✓ 100% completed
Task 2: Three experiments with and without oil 100% completed
Task 3: Copepod data evaluation 100% completed
Task 4: Chemical analysis & data evaluation 100% completed
Task 5: Manuscript 1: Oil avoidance 0% not started (milestone 6/30/2020)
Phase II: Dispersants and copepod contact 25% in progress
Task 6a: Experiments with dispersed oil (chemistry) 100% completed
Task 6b: Experiments with dispersed oil (copepod) 0% not started (planned March/May2020)
Task 7: Copepod data evaluation 0% not started (planned for Year 7)
Task 8: Chemical analysis & data evaluation 0% not started (planned for Year 7)
Phase III: Influence of Stratification 25% in progress
Task 9a: Set Exp. with stratification 100% in progress (milestone for End of March 2020)
Task 9b: Exp. with stratification (chemistry) + copepod) 0% not started (planned May/June 2020)
June/July 2020
COVID-19 changes:
ADAC Program Year 6 Annual Meeting 14 May 2020
Aug/Sept 2020

## Slide 18: Progress on Outcomes/Output
Update on feedback from Project Champion
and Other Engagement
Update on Transition and TRL
On track based on Project Champion and Advisors Group
Project Champion reviewed Task 1; data received Go-Ahead March 2020
Finish Research and Knowledge Product in Year 7
Transition is via Knowledge Product and TRL associated with Fundamental Research
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 19: Student contributions
Our goal is to bring 2 students onboard in June of 2020.
1st student will be responsible for:
Collection and maintaining of copepods
Analyzing video images of copepod distribution in the tanks
2nd Student will be responsible for
dispersant tests
collecting and analyzing hydrocarbon
Bigelow Summer Students
Plan modified due to COVID-19:
remote program for students (image and data analysis)
experiments will be performed by us
ADAC Program Year 6 Annual Meeting 14 May 2020

## Slide 20: Arctic Copepods: Questions?
Feedback…
What are we missing?
What can we improve?
Who should we connect with to improve odds of research success?
ADAC Program Year 6 Annual Meeting 14 May 2020