## Slide 1: ADAC Year 8 First Quarter Quarterly Review ...Via Conference Call, 23-24 September 2021 ADAC Project Briefing Marine IP - Detection and Mapping of Oil Under Ice: A Ruggedized Field Kit
Researcher Kari Walker, IntelliSense Marine LLC
PI Dr. Scott Socolofsky, Texas A&M University

## Slide 2: ADAC Project: Marine Induced Polarization Methods for the Detection and Mapping of Oil in an Arctic Marine Oil Spill – Ruggedized Field Kit Production and Testing
• Project Principal Investigator: Dr. Scott Socolofsky, Texas A&M University
• Supporting Team:
  Ms. Kari Walker and Mr. Kevin Hand, IntelliSense Marine
  Mr. Art Wright, Mr. Jay Radler and Mr. Todd Stedman, Induced Polarization Associates
  Mr. Nathan Lamie, Lead Engineer/Facility Operator, Cold Regions Research and Engineering Laboratory, U.S. Army Corps of Engineers
• Project Champion: LCDR Clifton Graham, CG-MER
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 3: Marine IP: Project Description and Baseline
Project Description: Federal on-scene spill responders need remote sensing tools to detect and map oil in the open-Arctic ocean, broken ice fields, as well as oil under and within ice.
This research effort will build and test hardware and software for an Arctic-Ready Marine Induced Polarization (Marine IP) System, which locates and assesses polarizable mineral and particle distributions - such as hydrocarbons - in water, ice and in sediment.
Baseline: Marine IP has shown strong promise to serve as a tool for the detection and mapping of oil under ice and in seafloor sediment. A robust, Arctic-Ready Marine IP system needs to be developed to mitigate the harsh conditions of the Arctic.
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 4: Marine IP: Method
Oil on and within seafloor sediment:
A cable is towed behind a vessel
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the return signal caused by substances encountered
Receiver Electrodes
Oil
Transmit Electrodes
Depressor
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 5: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility
A cable streamed under tank ice
Transmit electrodes emit a controlled electrical current
Receiver electrodes measure changes in the signal due to substances encountered
Induced Polarization Streamer Tail
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 6: Marine IP: Method
Oil-Under-Ice testing: CRREL Testing Facility:
Tests will be conducted using shared oil under ice conditions:
  Existing oil placement will be well documented
  Additional oil will be added under and encapsulated within the ice
CRREL Testing Facility
Control line
Transmit (red) and receive (green) electrodes
Buoys (yellow) provide flotation
Test Area
Test Area
Test Area
Water at 0.25 Salinity
Induced Polarization Streamer Tail
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 7: Marine IP: Progress on Research Objectives
Project Objectives:
Continue to validate Marine IP as a viable means to detect oil within ice and broken ice.
Develop and build the hardware, firmware and software for an Arctic-Ready Marine IP System that can withstand the harsh environment of the Arctic: Q1-Q2
Test the Arctic-Ready Marine IP System in an offshore, towed scenario: Feb 2022
Test the Arctic-Ready Marine IP System in a simulated Arctic environment scenario (CRREL): Feb 2022
Further identify possible Marine IP deployment mechanisms for characterization, with emphasis on AUVs: Q4
Old Enclosure
New Enclosure
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 8: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
Build.
Design.
Custom build of electronic boards complete.
Project Milestones – Hardware Designed and Built
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 9: Marine IP: Progress on Milestones
Design and write prototype firmware. 90% Complete
  Working to complete Transmitter Microcontroller, Touch UI Display
Display Interface: Build
Display Interface: Design
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 10: Marine IP: Progress on Milestones
  Fabricate prototype. Complete
Laptop
New Marine IP Enclosure
Marine IP Cable
GPS
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 11: Marine IP: Planned Field Work
Oil-Under-Ice testing: CRREL Testing Facility
Tests using shared oil under ice conditions:
CRREL Testing Facility
Open Water Testing: Puget Sound
Tests on a vessel in Puget Sound, WA:
Planned for February 2022
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 12: Marine IP: Progress on Milestones
Firmware developed and undergoing small-scale laboratory tests and bug fixes. October 15th
Startup and initial performance and function tests. October 22nd Hardware Complete. Pending firmware.
Submit Field Test Plans for HQ USCG Project Champion review and approval. In Progress
Complete performance and functional tests in laboratory. In Progress. Pending firmware.
Submit engineering report reviewing design, fabrication methods, construction, and initial performance reviews of hardware system. Complete. Will be update upon completion of firmware and testing.
Complete mockups of user interfaces and software control systems. In Progress Software will be revised for after completion of firmware and testing.
Hardware: Beach testing of device and its integrations with the Marine IP cables. November 2021
Complete implementation of Arctic-Ready Marine IP System – Hardware, Software. January 2022
Complete Field Trials of Arctic-Ready Marine IP System. February 2022
Complete data analysis and reporting. March 2022
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 13: Marine IP: Progress on Outcomes/Outputs
  Provide test plan for Arctic-Ready Marine IP System. December 2021 - January 2022
Arctic-Ready Marine IP System – Hardware: Provide a Marine IP measurement field kit designed for use in arctic conditions. December 2021
Arctic-Ready Marine IP System – Software: Provide a new software interface for data collection using the Marine IP measurement field kit. December 2021
Technical Report: Provide DHS with a report with all the results of this research that becomes publicly available. March 2022.
Engineering Design Report: Provide advanced information for the design parameters for applications of Marine IP with an autonomous underwater vehicle (AUV). March 2022
Peer-Reviewed Publications: Research team will produce draft peer-reviewed scientific publications from this project. 2022
Publicly Available Data: Researchers (in coordination with ADAC) will ensure all releasable data produced during this project is publicly available within 6 months of project conclusion. 2022
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 14: Marine IP: Progress on Remaining Year 6 Objectives
Remaining Project Objectives:
Investigate the potential of Marine IP to detect oil in partial ice formations as well as under pack ice.
Investigate and determine Marine IP’s effectiveness to accurately detect the extent of contaminated areas.
Remaining Project Milestones:
Determine the spectral signature of selected target contaminants utilizing the new Marine IP system.
Complete data analysis and reporting.
Old System
New System
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021

## Slide 15: Thank you!
Feedback…
What are we missing?
What can we improve?
Who should we connect with to improve odds of research success?
ADAC Program Year 8 First Quarter Quarterly Review 23-24 September 2021